## Slide 1: FAPI-SIG Community 11th Meeting
@Web Conference
20 Jan 2021

## Slide 2: Table of Contents
Major Topics
Status Updates from 10th Meeting
FAPI-RW
FAPI-CIBA (poll mode)
Client Policy Official Support
Future Topic Proposal

## Slide 3: Major Topics

## Slide 4: Major Topics
Project : FAPI-RW
OpenID Foundation will fix the final version of FAPI 1.0
(FAPI-RO -> FAPI 1.0 Baseline, FAPI-RW -> FAPI 1.0 Advanced).
Need to follow this final version of FAPI 1.0.
Project : Client Policy Official Support
Subproject : Client Policies for FAPI-RW
All PRs needed to support FAPI-RW by using only Client Policy have been merged.
Project : Client Policy Official Support
Subproject : External Interfaces
KEYCLOAK-16137 Client Policy : Support New Admin REST API
Its design document has been approved and merged.

## Slide 5: Status Updates from 10th Meeting FAPI-RW

## Slide 6: Remaining Issues Status
6 Jan 2021
4 Issues in total
3 Resolved
1 In Progress
0 Assigned
0 Not Assigned
20 Jan 2021
3 Resolved
1 In Progress
0 Assigned
0 Not Assigned
+0
+0
+0
+0

## Slide 7: Remaining Issues Details
[Conformance Test]
#39 Confirm all FAPI R/W OP w/ MTLS conformance tests are passed by the released keycloak
Resolved
#40 Confirm all FAPI R/W OP w/ Private key conformance tests are passed by the released keycloak
Resolved
[Conformance Test Environment]
#45 Integrating FAPI-RW conformance tests run into keycloak’s CI/CD pipeline
FAPI-RW conformance test run automation completed.
Integrating this automation onto keycloak codebase remains open.
#46 Consider alternative for keycloak-gatekeeper used in FAPI-RW conformance test run environment
Resolved

## Slide 8: Project Progress
Actual
Plan
2020
Sep
2021
Jan
Nov
31 Mar, M/S #2
All FAPI-RW Conformance Tests Passed
At the beginning of Sep 2020 : Kick off the activity
Oct
Dec
16
6
20
30 Nov, M/S #1
All FAPI-RW Pull-Requests Merged
25 Sep, M/S #1
Done : 16 of 16 issues resolved
M/S #2 / 9w AVAIL
20 of 21 issues resolved / 95%
0 of 21 issues assigned
1 of 21 work in progress
?
Mid 2021 RH-SSO 7.5 expected
Feb
Mar
Apr

## Slide 9: Last Stretch - Following Final version of FAPI 1.0
[Motivation]
The current keycloak (12.0.1) has supported FAPI-RW security profile which version is Implementer’s Draft ver 2(ID2). It also has passed all corresponding conformance tests on local environment.
On Jan, OID-F will fix the final version of FAPI 1.0 which have some changes compared with ID2.
IMO, we must support the final version of FAPI 1.0.
[Additional works needed]
We need to do the following works :
Clarify the difference between the final version and ID2
Clarify whether additional implementation is needed
If needed, implement features needed to support the final version of FAPI 1.0
Confirm whether the keycloak incorporating these features can pass all conformance tests for the final version of FAPI 1.0.
After PRs for such the implementation are merged and the new version of keycloak is released, confirm whether this version of keycloak can pass all conformance tests for the final version of FAPI 1.0.
[Milestone]
The works above need to be done by the end of Mar to meet the release of RH-SSO 7.5.

## Slide 10: FAPI Milestone
FAPI
1.0
Part 1
FAPI-RO
Part 2
FAPI-RW
Part 3 CIBA
Part 4 JARM
19 Feb 2017 : FAPI Part 1 Implementer’s Draft Approved*1
Final
2017
Feb
ID1
ID2
Oct
ID1
Final
2018
Jul
ID2
ID1
2019
Aug
ID1
2020
Oct
24 Jul 2017 : FAPI Part 2 Implementer’s Draft Approved*2
24 Oct 2018 : Implementer’s Drafts of Three FAPI Specifications
Approved *3
23 Aug 2019 : Implementer’s Draft of FAPI Client Initiated Backchannel Authentication (CIBA) Profile Approved *4
29 Oct 2020 - 28 Dec 2020 : Public Review Period for Proposed Final FAPI 1.0 Part 1 and Part 2 Specifications*5
*5 : https://openid.net/2020/10/29/public-review-period-for-proposed-final-fapi-1-0-part-1-and-part-2-specifications/
*4 : https://openid.net/2019/08/23/implementers-draft-of-fapi-client-initiated-backchannel-authentication-ciba-profile-approved/
https://openid.net/specs/openid-financial-api-ciba-ID1.html
*3 : https://openid.net/2018/10/24/implementers-drafts-of-three-fapi-specifications-approved/
http://openid.net/specs/openid-financial-api-part-1-ID2.html
http://openid.net/specs/openid-financial-api-part-2-ID2.html
http://openid.net/specs/openid-financial-api-jarm-ID1.html
*2 : https://openid.net/2017/07/24/fapi-part-2-implementers-draft-approved/
http://openid.net/specs/openid-financial-api-part-2-ID1.html
*1 : https://openid.net/2017/02/19/fapi-part-1-implementers-draft-approved/
http://openid.net/specs/openid-financial-api-part-1-ID1.html
Baseline
Advanced
29 Dec 2020 - 5 Jan 2021 : Vote for Proposed Final FAPI 1.0 Part 1 and Part 2 Specifications*6
*6 : https://openid.net/2020/11/30/notice-of-vote-for-proposed-final-fapi-1-0-part-1-and-part-2-specifications/
Dec
2021

## Slide 11: Status Updates from 10th Meeting FAPI-CIBA (poll mode)

## Slide 12: Remaining Issues Status
6 Jan 2021
13 Issues in total
8 Resolved [62%]
2 In Progress
3 Assigned
0 Not Assigned
20 Jan 2021
8 Resolved [62%]
2 In Progress
3 Assigned
0 Not Assigned
+0
+0
+0
+0

## Slide 13: Remaining Issues Details 1/3
[Backchannel Authentication Request]
#53 encrypt/decrypt login_hint
Resolved
#54 support login_hint_token
Resolved
#55 support id_token_hint
Resolved
#56 support Signed Authentication Request
In Review
#57 support User Code
Resolved

## Slide 14: Remaining Issues Details 2/3
[Settings]
#58 Realm Settings (CIBA Policy) overriden by Client Settings
In Review
[Internals]
#59 Use Only Auth Result Cache by Infinispan For CIBA Flow Session Binding
Resolved
#60 Use Only Auth Result Cache on Communication with Decoupled Auth Server
Resolved
#61 Token Request Throttling Information Not Cluster-wide Sync
Resolved
#62 Use Security Event Token (SET) as message format between keycloak and Decoupled Auth Server
Resolved

## Slide 15: Remaining Issues Details 3/3
[Arquillian Integration Test]
#63 Confirm CIBA Implementation Works Well in Clustering Environment
Assigned
#64 Confirm CIBA Implementation Works Well in Cross-DC Environment
Assigned
[Conformance Test]
#65 Establish the way of running FAPI-CIBA OP poll w/ MTLS and w/ Private Key against CIBA Implementation
Assigned

## Slide 16: Upstreaming CIBA Support
Pure CIBA
KEYCLOAK-12137 OpenID Connect Client Initiated Backchannel Authentication (CIBA)
CIBA Implementation based on its prototype (tnorimat/ciba-prototype)
#59 Use Only Auth Result Cache by Infinispan For CIBA Flow Session Binding
#60 Use Only Auth Result Cache on Communication with Decoupled Auth Server
#61 Token Request Throttling Information Not Cluster-wide Sync
PR Sent
FAPI-CIBA
#57 support User Code
FAPI-CIBA
#54 support login_hint_token
FAPI-CIBA
#55 support id_token_hint
FAPI-CIBA
#53 encrypt/decrypt login_hint
…

## Slide 17: Project Progress
Actual
Plan
2020
Sep
2021
Jan
Nov
31 Mar, M/S #2
All FAPI-CIBA (poll) Conformance Tests Passed
At the beginning of Sep 2020 : Kick off the activity
Oct
Dec
31 Jan, M/S #1
All FAPI-CIBA (poll) Pull-Requests Merged
Mid 2021 RH-SSO 7.5 expected
M/S #1 / 1w AVAIL
8 of 13 issues resolved / 62%
5 of 13 issues assigned
Feb
Mar
Apr
?
6
20
3
17
3
17
M/S #2 / 11w AVAIL
0 of 1 issues resolved / 0%
1 of 1 issues assigned
will re-schedule : by 28 Feb

## Slide 18: Status Updates from 10th Meeting Client Policy Official Support

## Slide 19: Subprojects
[Mandatory]
External Interfaces
Client Policies for FAPI-RW
[Optional]
Built-in Default Client Policies
Client Registration Policies Migration
Pend
Active
Completed
Active

## Slide 20: Issues Status - External Interfaces
6 Jan 2021
6 Issues in total
0 Resolved [0%]
2 In Progress
1 Assigned
3 Not Assigned
20 Jan 2021
1 Resolved [17%]
1 In Progress
1 Assigned
3 Not Assigned
+1
-1
+0
+0

## Slide 21: Issue status in detail : External Interfaces
KEYCLOAK-16137 Client Policy : Support New Admin REST API (Design)
  KEYCLOAK-16805 Client Policy : Support New Admin REST API (Implementation)
KEYCLOAK-16138 Client Policy : Support New Admin Console UI (Design)
    Concept Design by RH UXD team : https://marvelapp.com/prototype/6e70eh2/screen/74918976
KEYCLOAK-16847 Client Policy : Support New Admin Console UI (Implementation)
KEYCLOAK-14209 Client Policy : UI on Admin Console
KEYCLOAK-14211 Client Policy : Remove Client Policy related individual settings on Admin Console
[Potential Blocking Factor]
New Admin Console Release (not yet released)
In Progress
Resolved

## Slide 22: Issue status in detail : External Interfaces
PR in Review
In
Develop
Ready to Send PR
PR
Sent
PR
Merged
KEYCLOAK-16137
1 of 6 :
Resolved
KEYCLOAK-16805
New Admin REST API
KEYCLOAK-14209
Existing Admin Console
Design
Impl
KEYCLOAK-16138
KEYCLOAK-16847
New Admin Console
Design
Impl
KEYCLOAK-14211
follows
New Admin Console Release
Outside FAPI-SIG
follows

## Slide 23: Issues Status - Client Policies for FAPI-RW
6 Jan 2021
17 Issues in total
15 Resolved [88%]
2 In Progress
0 Assigned
0 Not Assigned
20 Jan 2021
17 Issues in total
17 Resolved [100%]
2 In Progress
0 Assigned
0 Not Assigned
+2
-2
+0
+0
Completed

## Slide 24: Issue status in detail : Client Policies for FAPI-RW
KEYCLOAK-14190 Client Policy - Condition : The way of creating/updating a client
KEYCLOAK-14191 Client Policy - Condition : Author of a client - User Group
KEYCLOAK-14192 Client Policy - Condition : Author of a client - User Role
KEYCLOAK-14193 Client Policy - Condition : Client - Client Access Type
KEYCLOAK-14194 Client Policy - Condition : Client - Client Domain Name
KEYCLOAK-14195 Client Policy - Condition : Client - Client Role
KEYCLOAK-14196 Client Policy - Condition : Client - Client Scope
KEYCLOAK-14197 Client Policy - Condition : Client - Client Host
KEYCLOAK-14198 Client Policy - Condition : Client - Client IP
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Slide 25: Issue status in detail : Client Policies for FAPI-RW
KEYCLOAK-14199 Client Policy - Executor : Enforce more secure client authentication method when client registration
KEYCLOAK-14200 Client Policy - Executor : Enforce Holder-of-Key Token
KEYCLOAK-14201 Client Policy - Executor : Enforce Proof Key for Code Exchange (PKCE)
KEYCLOAK-14202 Client Policy - Executor : Enforce secure signature algorithm for Signed JWT client authentication
KEYCLOAK-14203 Client Policy - Executor : Enforce HTTPS URIs
KEYCLOAK-14204 Client Policy - Executor : Enforce Request Object satisfying high security level
KEYCLOAK-14205 Client Policy - Executor : Enforce Response Type of OIDC Hybrid Flow
KEYCLOAK-14206 Client Policy - Executor : Enforce more secure state and nonce treatment for preventing CSRF
KEYCLOAK-14207 Client Policy - Executor : Enforce more secure client signature algorithm when client registration
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Slide 26: Issue status in detail : Client Policies for FAPI-RW
PR in Review
KEYCLOAK-14198
KEYCLOAK-14206
KEYCLOAK-14199
KEYCLOAK-14190
In
Develop
Ready to Send PR
PR
Sent
PR
Merged
KEYCLOAK-14195
KEYCLOAK-14204
KEYCLOAK-14205
KEYCLOAK-14201
KEYCLOAK-14196
KEYCLOAK-14207
KEYCLOAK-14193

## Slide 27: Issue status in detail : Client Policies for FAPI-RW
PR in Review
In
Develop
Ready to Send PR
PR
Sent
PR
Merged
KEYCLOAK-14197
KEYCLOAK-14191
KEYCLOAK-14192
KEYCLOAK-14203
KEYCLOAK-14200
KEYCLOAK-14202
17 of 17 :
Resolved

## Slide 28: Issues Status - Client Registration Policies Migration
6 Jan 2021
3 Issues in total
0 Resolved [0%]
3 In Progress
0 Assigned
0 Not Assigned
20 Jan 2021
0 Resolved [0%]
9 In Progress
0 Assigned
1 Not Assigned
+0
+6
+0
+1

## Slide 29: Issue status in detail : Client Registration Policies Migration
KEYCLOAK-15533 Client Policy : Extends Policy Interface to Migrate Client Registration Policies
KEYCLOAK-15534 Client Policy : Implement Existing Client Registration Policies as Client Policies
KEYCLOAK-16806 Client Policy : Implement existing "ClientDisabledClientRegistrationPolicy" as Client Policies' executor
KEYCLOAK-16807 Client Policy : Implement existing "ClientScopesClientRegistrationPolicy" as Client Policies' executor
KEYCLOAK-16808 Client Policy : Implement existing "ConsentRequiredClientRegistrationPolicy" as Client Policies' executor
KEYCLOAK-16809 Client Policy : Implement existing "MaxClientsClientRegistrationPolicy" as Client Policies' executor
KEYCLOAK-16810 Client Policy : Implement existing "ProtocolMappersClientRegistrationPolicy" as Client Policies' executor
KEYCLOAK-16811 Client Policy : Implement existing "ScopeClientRegistrationPolicy" as Client Policies' executor
KEYCLOAK-16812 Client Policy : Implement existing "TrustedHostClientRegistrationPolicy" as Client Policies' executor
KEYCLOAK-14210 Client Policy : Migrate Client Registration Policies to Client Policies
PR Sent
PR Ready
PR Ready
PR Ready
PR Ready
PR Ready
PR Ready
PR Ready

## Slide 30: Issue status in detail : Client Registration Policies Migration
PR in Review
KEYCLOAK-16811
KEYCLOAK-16812
KEYCLOAK-16809
KEYCLOAK-15533
In
Develop
Ready to Send PR
PR
Sent
PR
Merged
KEYCLOAK-16806
KEYCLOAK-16807
KEYCLOAK-16808
KEYCLOAK-16810
KEYCLOAK-14210
Wait for being merged
Wait for being merged
Wait for being merged
Wait for being merged
Wait for being merged
Wait for being merged
Wait for being merged
Extends
Interfaces
KEYCLOAK-
15534
Migrate 7
Registration
Policies
1 of 10 :
PR Sent

## Slide 31: Project Progress
Actual
Plan
2020
Sep
2021
Jan
Nov
31 Mar, M/S #2
Client Policy Available on New Admin Console
At the beginning of Sep 2020 : Kick off the activity
Oct
Dec
28 Feb, M/S #1
Client Policy Available on Existing Admin Console
M/S #1 / 7w AVAIL
1 of 6 issues resolved / 16%
Feb
Mar
Apr
6
20
3
17
3
17
M/S #3
Client Policy Available for FAPI-RW
Done M/S #3 / 9w AVAIL
13 of 13 issues resolved / 100%
M/S #2 / 11w AVAIL
0 of 2 issues resolved / 0%
Completed

## Slide 32: Future Topic Proposal

## Slide 33: Keycloak PSD2 support
“Try to make keycloak (+ other external components if needed) comply with PSD2”
PSD2
Support requirements from eIDAS
TPP’s QWAC verification of Client Authentication on TLS layer
1. Confirm that TPP’s certificate is QWAC that was issued from QTSP.
2. Confirm that TPP’s certificate as QWAC does not expire and was not revoked.
3. Confirm that TPP’s certificate follows QWAC profile.
4. Confirm that what TPP’s certificate as QWAC states is true (roles, PSP ID).

## Slide 34: Keycloak PSD2 support - Current Status
PSD2
Support requirements from eIDAS
TPP’s QWAC verification of Client Authentication on TLS layer
1. Confirm that TPP’s certificate is QWAC that was issued from QTSP.
-> It can realize it by using only QTSP’s certificates as keycloak’s trust anchors and manage them.
2. Confirm that TPP’s certificate as QWAC does not expire and was not revoked.
-> The end user authentication by X.509 has already supported revocation check by CRL/OCSP while the client authentication by X.509 not.
3. Confirm that TPP’s certificate follows QWAC profile.
4. Confirm that what TPP’s certificate as QWAC states is true (roles, PSP ID).

## Slide 35: END